## Read me
Earnival — User Acceptance Testing
Fill this in during the UAT round that runs before your first real event.
HOW TO RUN IT
1. Assign testers | You need at least 3: one organiser, one vendor, one attendee who has never seen the product.
2. Use real phones | Not a desktop browser resized. Buying and checking in are phone activities — test them on phones.
3. Work through 'Test cases' | Set Result to Pass, Fail or Blocked. A test you did not run stays 'Not tested'.
4. Every Fail gets a bug | Raise it on 'Bug log', then put its Bug ID back on the test case row.
5. Check 'Known issues' first | Things already found and triaged. Do not raise these again.
6. Sign off | The gate criteria on 'Sign-off' decide whether you launch.
SEVERITY — what the words mean
S1 Critical | Money is wrong, data is exposed, or the core journey is impossible. Stops launch.
S2 Major | A journey is broken but has a workaround. Stops launch unless the workaround is acceptable on the night.
S3 Minor | Wrong, annoying, but nobody loses money or gets stuck. Fix after launch.
S4 Cosmetic | Visual or wording. Backlog.
WHAT COUNTS AS S1
A split that does not sum to the amount charged. A ticket that scans twice. A refund that moves in the app but not in the bank. Someone seeing another person's money. A payment marked paid without a Paystack webhook.
PROGRESS
Total test cases | 65
Passed | 0
Failed | 0
Blocked | 0
Not tested | 65
P0 cases still not passed | 58
Open S1 bugs | 0
Open S2 bugs | 1
These update themselves as the other two sheets are filled in.

## Test cases
Test cases — set Result on every row. Yellow columns are yours to fill in.
ID | Journey | Pri | Device | Steps | Expected result | Req | Result | Tester | Date | Bug ID | Notes
TC-001 | Buy a ticket | P0 | Phone | Open the event link. Pick 2 Regular tickets. Enter name, email, phone. Pay with a real card. | Payment succeeds and you land on a confirmation with your ticket reference. | DSC-01 | Not tested
TC-002 | Buy a ticket | P0 | Phone | Complete a purchase, then check the email inbox. | Ticket email arrives within 2 minutes, in the inbox and not in spam, with a scannable QR and a check-in code. | DSC-07 | Not tested
TC-003 | Buy a ticket | P0 | Phone | Buy without creating an account. | No sign-up is ever demanded. The purchase completes with name, email and phone only. | DSC-03 | Not tested
TC-004 | Buy a ticket | P0 | Phone | Before paying, read the page for the refund policy. | The refund policy is visible before the pay button, not only in the terms. | DSC-08 | Not tested
TC-005 | Buy a ticket | P0 | Phone | Try to buy more tickets than remain on a nearly sold-out type. | The quantity stepper caps at what is left. You cannot exceed it. | DSC-03 | Not tested
TC-006 | Buy a ticket | P0 | Phone | Start checkout, then abandon it. Wait 25 minutes. Reload the event page. | The held tickets are back on sale. | DSC-04 | Not tested
TC-007 | Buy a ticket | P1 | Phone | Two people buy the last ticket at the same moment. | Exactly one succeeds. The other gets a clear sold-out message, not an error page. | DSC-05 | Not tested
TC-008 | Buy a ticket | P0 | Phone | Pay with a card you know will be declined. | You are told the payment failed and can retry. No ticket is issued. | PAY-09 | Not tested
TC-009 | Ticket | P0 | Phone | Open the ticket link from the email. | The badge shows the QR, check-in code, ticket type, your name, and the organiser's note. | DSC-07 | Not tested
TC-010 | Ticket | P0 | Phone | Screenshot the badge and close the email. | The screenshot alone is enough to get in. Confirm at check-in. | DSC-07 | Not tested
TC-011 | Ticket | P0 | Phone | Go to 'Find my ticket'. Enter the email you bought with. | A recovery link arrives by email and opens your tickets. | DSC-09 | Not tested
TC-012 | Ticket | P0 | Phone | Go to 'Find my ticket'. Enter an email that bought nothing. | The response is identical to the one above. It must not reveal whether the address exists. | DSC-10 | Not tested
TC-013 | Buy from a shop | P0 | Phone | From the event page, open a connected shop and add items to the basket. | Items add, quantities adjust, and the total updates with the processing fee shown separately. | ORD-01 | Not tested
TC-014 | Buy from a shop | P0 | Phone | Build a basket with items from two different shops. Pay once. | One payment. You receive a separate order reference per shop. | ORD-02 | Not tested
TC-015 | Buy from a shop | P0 | Phone | Check the vendor's console after that purchase. | Each vendor sees only their own items — never the other shop's. | ORD-02 | Not tested
TC-016 | Buy from a shop | P0 | Phone | Place a pay-at-event order where the shop allows it. | The order is created without payment and shows as due at the counter. | ORD-04 | Not tested
TC-017 | Buy from a shop | P0 | Phone | Open the order tracking link. | Status is visible and updates as the vendor moves the order along. | ORD-11 | Not tested
TC-018 | Fulfilment | P0 | Phone | As the vendor, mark a paid order Ready. | The buyer receives a pickup code. | ORD-07 | Not tested
TC-019 | Fulfilment | P0 | Phone | As the vendor, try to complete an order without the buyer's pickup code. | It is refused. The code must be entered and matched. | ORD-07 | Not tested
TC-020 | Fulfilment | P0 | Phone | Complete one shop's order in a two-shop basket. | Only that shop's order completes. The other is untouched. | ORD-09 | Not tested
TC-021 | Fulfilment | P1 | Phone | Place an order and watch the vendor's phone. | A sale alert arrives on WhatsApp, or by SMS if WhatsApp is unavailable. | ORD-12 | Not tested
TC-022 | Check-in | P0 | Phone | As door staff, scan a valid ticket QR with the phone camera. | Green pass, the guest's name, and the counter increments. | OPS-01 | Not tested
TC-023 | Check-in | P0 | Phone | Scan the same ticket a second time. | Refused, and it says when the guest was already checked in. | OPS-04 | Not tested
TC-024 | Check-in | P0 | Phone | Type the check-in code by hand instead of scanning. | Same result as a scan. This is the dead-battery path. | OPS-03 | Not tested
TC-025 | Check-in | P0 | Phone | Search the guest list by name and check someone in from there. | The guest is found and checked in. | OPS-03 | Not tested
TC-026 | Check-in | P0 | Phone | Put the phone in aeroplane mode. Scan three tickets. Turn connectivity back on. | All three queue offline, then sync. The counter is correct and nobody is double-registered. | OPS-05 | Not tested
TC-027 | Check-in | P0 | Phone | Scan a refunded or cancelled ticket. | Refused, with the reason stated. | OPS-08 | Not tested
TC-028 | Check-in | P0 | Phone | Sign in as door staff and try to reach the revenue figures. | You are sent to the scanner. Revenue is never shown to door staff. | TEAM-03 | Not tested
TC-029 | Check-in | P0 | Phone | Sign in as someone who is not on the door team and open the scan URL directly. | Access is refused. | OPS-07 | Not tested
TC-030 | Check-in | P1 | Phone | Stand at arm's length in daylight and scan. | The pass or fail is readable at arm's length, with sound and vibration. | OPS-06 | Not tested
TC-031 | Organiser | P0 | Both | Create an event with a banner, two ticket types and a venue. Publish it. | A public event page exists at a stable URL, with a QR and share links. | EVT-01 | Not tested
TC-032 | Organiser | P0 | Phone | Paste the event link into a WhatsApp chat. | It unfurls with a real preview image, title and date — not a bare URL. | EVT-03 | Not tested
TC-033 | Organiser | P0 | Both | Change the venue on a published event with tickets already sold. | The change saves, existing tickets stay valid, and you are prompted to email ticket holders. | EVT-04 | Not tested
TC-034 | Organiser | P0 | Both | Try to reduce a ticket type's capacity below the number already sold. | Refused. | EVT-06 | Not tested
TC-035 | Organiser | P0 | Both | Reprice a ticket type after some have sold. | Only future sales use the new price. Money already taken is unchanged. | EVT-06 | Not tested
TC-036 | Organiser | P0 | Both | Open the console after some traffic. | Ticket revenue, share of shop sales, tickets sold, check-in progress and the funnel all show real numbers. | EVT-09 | Not tested
TC-037 | Organiser | P0 | Both | Invite a second person as door staff by email. | They receive an invitation and can check guests in once they accept — not before. | TEAM-01 | Not tested
TC-038 | Organiser | P0 | Both | Revoke that person's access mid-event. | They immediately lose the ability to check anyone in. | TEAM-02 | Not tested
TC-039 | Organiser | P1 | Both | Cancel an event that has sold tickets and paid orders. | Every outstanding ticket and paid order is refunded. Buyers are told. | EVT-11 | Not tested
TC-040 | Vendor | P0 | Both | Create a shop, add a product with a photo and a price, and publish. | The shop goes live with its own URL and QR. | SHP-01 | Not tested
TC-041 | Vendor | P0 | Both | Request a connection to a live event, offering a revenue share. | Before sending, you see exactly what each party receives on a sample sale. | CON-01 | Not tested
TC-042 | Vendor | P0 | Both | As the organiser, review and accept that request. | The worked example is shown again. Accepting makes the shop purchasable through the event. | CON-02 | Not tested
TC-043 | Vendor | P0 | Phone | Try to buy from a shop that has no active connection to the event. | Not purchasable through that event. | CON-03 | Not tested
TC-044 | Vendor | P1 | Both | Drop a product's stock below its low-stock threshold. | The vendor gets an alert. | SHP-07 | Not tested
TC-045 | Money | P0 | Both | Buy a NGN 10,000 item from a shop on a 5% connection. Write down every figure. | Buyer charged 10,150. Platform 750, organiser 500, vendor 8,750. The parts sum to the gross exactly. | PAY-06 | Not tested
TC-046 | Money | P0 | Both | Compare the vendor's settlement breakdown against the orders that produced it. | Gross, service charge, organiser share and net all reconcile. No rounding is lost. | PAY-05 | Not tested
TC-047 | Money | P0 | Both | Issue a full refund on a paid ticket. | The buyer is made whole. Stock returns to the pool. The money leaves the Paystack balance. | PAY-13 | Not tested
TC-048 | Money | P0 | Both | Issue a partial refund, then try to refund more than remains. | The second attempt is refused. | PAY-14 | Not tested
TC-049 | Money | P0 | Both | Try to refund a ticket that has already been scanned in. | Refused — the goods were delivered. | PAY-16 | Not tested
TC-050 | Money | P0 | Both | Run settlement, then check the destination bank account. | The payout lands, matches the app's figure to the kobo, and the payable balance drops accordingly. | PAY-20 | Not tested
TC-051 | Money | P0 | Both | Add a bank account whose name does not match the account holder. | Refused before it can ever receive money. | PAY-25 | Not tested
TC-052 | Verification | P0 | Both | As a new L0 user, create a paid event. | It does not go on sale until an admin approves it. | VRF-01 | Not tested
TC-053 | Verification | P0 | Both | Verify a phone number to reach L1, then open a shop. | L1 is granted and shop creation unlocks. | VRF-02 | Not tested
TC-054 | Verification | P0 | Both | Submit a BVN, then look at it again anywhere in the product. | Only the last four digits are ever shown — to you and to reviewers. | VRF-07 | Not tested
TC-055 | Verification | P0 | Both | Sell past your level's revenue cap on one event. | Checkout is blocked with a message naming the headroom left. | VRF-05 | Not tested
TC-056 | Verification | P0 | Both | Try to submit identity documents without a verified phone. | Refused. The levels are sequential. | VRF-08 | Not tested
TC-057 | Admin | P0 | Desktop | Sign in as a non-admin and open the admin URL directly. | Access refused. | ADM-04 | Not tested
TC-058 | Admin | P0 | Desktop | Approve a pending paid event. | It goes on sale and appears in discovery. | ADM-01 | Not tested
TC-059 | Admin | P0 | Desktop | Open the health endpoint. | It reports the database as reachable and lists which integrations are configured. | ADM-05 | Not tested
TC-060 | Cross-cutting | P0 | Phone | Open every public page on a 320px-wide phone. | Nothing scrolls sideways. All text is readable without zooming. | LEG-21 | Not tested
TC-061 | Cross-cutting | P0 | Phone | Pinch to zoom on the event page. | Zoom works. It is not blocked. | LEG-21 | Not tested
TC-062 | Cross-cutting | P0 | Phone | Turn the phone to landscape on the scanner and the event page. | Layout adapts. Nothing is cut off. | LEG-21 | Not tested
TC-063 | Cross-cutting | P0 | Both | Send a ticket email to a Gmail, a Yahoo and an Outlook address. | All three arrive in the inbox, not spam. This is the one that quietly kills launches. | NTF-01 | Not tested
TC-064 | Cross-cutting | P1 | Phone | Load the event page on a 3G connection. | It is usable within a few seconds. Images do not block the ticket buttons. | — | Not tested
TC-065 | Cross-cutting | P1 | Both | Navigate the checkout using only the keyboard. | Every control is reachable and the focused element is always visible. | LEG-21 | Not tested

## Bug log
Bug log — one row per defect. Row 3 is a worked example; overwrite or delete it.
Bug ID | Date found | Reporter | Severity | Device / browser | Where (URL or screen) | Steps to reproduce | What you expected | What actually happened | Screenshot / video link | Status | Owner | Fixed in / notes
BUG-001 | 2026-08-20 | Amara (vendor) | S2 Major | iPhone 13, Safari 17 | /s/amaras-grill — basket | 1. Open the shop from the event page 2. Add 3 Suya Platters 3. Tap Pay now 4. Complete payment with test card | Order confirmation with a reference | Spinner never stops. Payment was taken — it shows in Paystack — but no order appeared for 4 minutes. | (paste link) | Open | Eng

## Known issues
Known issues — already found and triaged. Do not raise these again.
Measured on 2026-08-11 by an automated sweep of 16 routes at 7 widths from 320px to 1440px, plus the build-status review in the PRD.
ID | Area | Severity | What it is | Evidence | Blocks launch?
KI-01 | Payments | S1 Critical | Never tested against live Paystack. Every payment, refund and transfer so far has run against sandbox stubs. | PRD PAY-28, marked P0 and not built. | YES
KI-02 | Compliance | S1 Critical | The data protection impact assessment for BVN/NIN collection has not been done. | PRD LEG-09, marked launch-blocking. | YES — blocks L2 only
KI-03 | Payouts | S1 Critical | Paystack Transfers require an OTP by default. If that setting is on, a payout appears to succeed and then hangs forever. | Known Paystack behaviour; not yet verified on the live dashboard. | YES
KI-04 | Email | S2 Major | The sending domain has no SPF/DKIM records yet, so ticket emails will land in spam. | Deliverability is untested from a verified domain. | YES
KI-05 | Accessibility | S3 Minor | Some controls are shorter than the 36px tap target the product's own spec claims: 'Go back' is 32x32, 'Edit' 24x20, the BVN/NIN and Door staff/Cohost toggles are 32-34px tall, header links 30px. | Automated sweep, 16 routes x 7 widths. | No
KI-06 | Accessibility | S3 Minor | Badge and label text renders at 11px in several places against the product's own stated 12px floor — 'Live', 'Open', 'Bought', 'Food & Drinks' and similar. | Same sweep. | No
KI-07 | Admin | S3 Minor | There is no audit log of admin actions. Approvals, KYC decisions and refunds leave no trail beyond the row they change. | PRD ADM-08. | No — but required before a second admin
KI-08 | Admin | S3 Minor | Admin rights can only be granted by direct SQL. There is no bootstrap screen. | PRD ADM-10. | No
KI-09 | Money | S3 Minor | Refunds have no time limit. A buyer can request one indefinitely. | PRD open decision #33. | No — decide the policy
KI-10 | Money | S2 Major | Nothing reconciles Earnival's own bank balance against the ledger. The ledger is internally consistent but unchecked against reality. | PRD review finding #5. | No — but do it early
KI-11 | Money | S3 Minor | Chargebacks are not modelled at all, and Paystack will pass them through. | PRD open decision #34. | No
KI-12 | Pricing | S3 Minor | Plan tiers (Standard 5%, Premium 2%) are specified but not built. Only the 7.5% rate is live. | PRD PAY-08. | No
KI-13 | Infrastructure | S2 Major | Rate limits key on a spoofable header. A determined attacker could deny inventory. | PRD risk register. | No — put Cloudflare in front
KI-14 | Infrastructure | S1 Critical | The 15-minute cron sweep is a single point of failure. If it stops, reservations are never released and nobody is paid. | PRD risk register. | YES — needs uptime monitoring

## Sign-off
Launch gate
Every line must read YES before the link goes to anyone outside the pilot cohort.
# | Gate criterion | Met? | Evidence / who confirmed | Date
1 | Every P0 test case is marked Pass.
2 | There are no open S1 bugs.
3 | There are no open S2 bugs, or each one has a workaround the organiser has accepted in writing.
4 | One real event has run end to end on live Paystack keys — a real card charged, a real ticket scanned, a real payout landed in a real bank account.
5 | Paystack Transfers OTP has been checked on the live dashboard and payouts are confirmed to complete.
6 | The sending domain is verified with SPF and DKIM, and a test ticket reached Gmail, Yahoo and Outlook inboxes.
7 | The Paystack webhook URL is registered against the live domain and a delivery has been observed succeeding.
8 | The cron sweep is scheduled and has been observed running, with uptime monitoring alerting if it stops.
9 | Terms, privacy policy and refund policy are published at the live domain and reachable from checkout.
10 | The DPIA is complete — or Level 2 verification is switched off until it is.
11 | A named human is on call for the event, with the admin console reachable from a phone.
12 | A rollback plan exists: what you tell buyers, and how you refund everyone, if the event has to be abandoned mid-way.
| Gates met | 0
| Gates outstanding | 12
Signed off by
Name
Role
Date